## Read Me
Phase 4 ¦ Source Qualification
Migration Factory and Domain Waves
Qualification rule | Gates 0-1 only. A Fail at either gate blocks qualification.
Later stages | Gates 2-6 govern mapping, dry run, production entry, acceptance, and closure.
Candidate rule | Phase 3 carry-forwards remain proof candidates until source and owner facts are verified.
Priority score | Value + reuse + (6 - complexity). Higher scores receive earlier review.
Score use | Prioritize assessment only. Scores do not approve wave assignment or override gates.
Next action | Confirm authoritative inventory, then document source facts, evidence, and owners.
Current qualification result | Count
Ready for mapping | 0
Ready with remediation | 0
Deferred | 0
Blocked | 0
In progress | 0
Disposition required | 0
Not assessed | 3
Rating guidance | Use 1, 3, and 5 as low, moderate, and high anchors; 2 and 4 are intermediate.
Business value | 1 limited; 3 material; 5 critical to the intended use.
Reuse value | 1 candidate-specific; 3 reusable by several consumers; 5 reusable across domains.
Complexity | 1 low; 3 moderate; 5 high, considering dependencies, transformation, and recovery.
Tie-breaks | For equal scores, favor lower cutover coupling, stable schema, and available owners.

## Source Register
Phase 4 ¦ Source Register
Enter one source or tightly related source group per row. Yellow cells are inputs; qualification status and priority score are calculated.
Candidate ID | Candidate / proof | Type | Known status | Source system | Business owner | Data steward | Technical owner | Consumer / intended use | Sensitivity / handling | Business value (1-5) | Reuse value (1-5) | Complexity (1-5) | Priority score (3-15) | Qualification status (Gates 0-1) | Gate 1 disposition | Proposed wave | Next action | Evidence / rationale
P01 | Inspection Completion | Proof candidate | Not deployed or executed; workspace had expired | [10 empty] | NOT ASSESSED |  |  | Re-establish source, owner, use, and execution environment; then decide whether to rerun proof. | Phase 3 closeout context; verify against repository
P02 | Application Processing Time | Proof candidate | Deterministic proof outstanding | [10 empty] | NOT ASSESSED |  |  | Identify source, owner, business definition, output, and validation criteria. | Phase 3 closeout context; verify against repository
P03 | Portability Activity | Proof candidate | Deterministic proof outstanding | [10 empty] | NOT ASSESSED |  |  | Identify source, owner, business definition, output, and validation criteria. | Phase 3 closeout context; verify against repository

## Gate Checklist
Phase 4 ¦ Factory Gate Checklist
Record a status only when the exit evidence exists. Gates 0-1 set source qualification; Gates 2-6 govern design through closure.
Candidate ID | Gate # | Factory stage | Status | Evidence / reference | Owner | Target date | Open issue / notes | Exit evidence / decision
P01 | 0 | Intake accepted | Not assessed |  |  |  |  | Owners confirm source/domain, use, consumers, scope, entities, dates, volume/update pattern, dependencies, handling constraints, and open questions.
P01 | 1 | Source qualified | Not assessed |  |  |  |  | Assess schema/keys/quality, history and change behavior, extract boundary/repeatability, lineage/security, support, dependencies, and reconciliation limits. Record disposition in Source Register.
P01 | 2 | Mapping and acceptance design approved | Not assessed |  |  |  |  | Approve versioned mapping and transformation rules, late/corrected/deleted-record handling, exception and reconciliation rules, required security review, consumer criteria, cutover/rollback triggers, and rollback owner.
P01 | 3 | Dry run ready | Not assessed |  |  |  |  | Record bounded scope and source boundary, run ID/configuration, logs and duration, reconciliation and exceptions, restart/replay proof, rollback steps, and open blockers.
P01 | 4 | Production wave entry | Not assessed |  |  |  |  | Confirm Gates 0-3 approvals, change window and operators, source retention, monitoring/evidence owners, reconciliation owner, rollback triggers, and decision authority.
P01 | 5 | Reconciliation and acceptance | Not assessed |  |  |  |  | Record source-target counts and controls, tolerances/exclusions, key and required-field checks, trace samples, exception dispositions, consumer validation, and acceptance or rollback decision.
P01 | 6 | Wave closed | Not assessed |  |  |  |  | Record final approval or rollback, reconciliation and exception disposition, source-retention and rollback-window end, evidence location/retention owner, lessons, and owned follow-ups.
P02 | 0 | Intake accepted | Not assessed |  |  |  |  | Owners confirm source/domain, use, consumers, scope, entities, dates, volume/update pattern, dependencies, handling constraints, and open questions.
P02 | 1 | Source qualified | Not assessed |  |  |  |  | Assess schema/keys/quality, history and change behavior, extract boundary/repeatability, lineage/security, support, dependencies, and reconciliation limits. Record disposition in Source Register.
P02 | 2 | Mapping and acceptance design approved | Not assessed |  |  |  |  | Approve versioned mapping and transformation rules, late/corrected/deleted-record handling, exception and reconciliation rules, required security review, consumer criteria, cutover/rollback triggers, and rollback owner.
P02 | 3 | Dry run ready | Not assessed |  |  |  |  | Record bounded scope and source boundary, run ID/configuration, logs and duration, reconciliation and exceptions, restart/replay proof, rollback steps, and open blockers.
P02 | 4 | Production wave entry | Not assessed |  |  |  |  | Confirm Gates 0-3 approvals, change window and operators, source retention, monitoring/evidence owners, reconciliation owner, rollback triggers, and decision authority.
P02 | 5 | Reconciliation and acceptance | Not assessed |  |  |  |  | Record source-target counts and controls, tolerances/exclusions, key and required-field checks, trace samples, exception dispositions, consumer validation, and acceptance or rollback decision.
P02 | 6 | Wave closed | Not assessed |  |  |  |  | Record final approval or rollback, reconciliation and exception disposition, source-retention and rollback-window end, evidence location/retention owner, lessons, and owned follow-ups.
P03 | 0 | Intake accepted | Not assessed |  |  |  |  | Owners confirm source/domain, use, consumers, scope, entities, dates, volume/update pattern, dependencies, handling constraints, and open questions.
P03 | 1 | Source qualified | Not assessed |  |  |  |  | Assess schema/keys/quality, history and change behavior, extract boundary/repeatability, lineage/security, support, dependencies, and reconciliation limits. Record disposition in Source Register.
P03 | 2 | Mapping and acceptance design approved | Not assessed |  |  |  |  | Approve versioned mapping and transformation rules, late/corrected/deleted-record handling, exception and reconciliation rules, required security review, consumer criteria, cutover/rollback triggers, and rollback owner.
P03 | 3 | Dry run ready | Not assessed |  |  |  |  | Record bounded scope and source boundary, run ID/configuration, logs and duration, reconciliation and exceptions, restart/replay proof, rollback steps, and open blockers.
P03 | 4 | Production wave entry | Not assessed |  |  |  |  | Confirm Gates 0-3 approvals, change window and operators, source retention, monitoring/evidence owners, reconciliation owner, rollback triggers, and decision authority.
P03 | 5 | Reconciliation and acceptance | Not assessed |  |  |  |  | Record source-target counts and controls, tolerances/exclusions, key and required-field checks, trace samples, exception dispositions, consumer validation, and acceptance or rollback decision.
P03 | 6 | Wave closed | Not assessed |  |  |  |  | Record final approval or rollback, reconciliation and exception disposition, source-retention and rollback-window end, evidence location/retention owner, lessons, and owned follow-ups.

## Source Profile
Phase 4 ¦ Source Profile
Complete one row per candidate. Leave unknown facts blank, record evidence, and do not promote proof candidates to production sources without owner validation.
Candidate ID | Candidate / proof | Type | Business domain | Source system | Entities / data objects | In-scope dates / history | Volume / growth | Update cadence / late arrivals | Upstream dependencies | Downstream consumers | Schema stability / change history | Keys / quality profile | Extraction method / source boundary | Restart / replay approach | Lineage / provenance available | Sensitivity / classification | Access / boundary constraints | Retention requirements | Reconciliation method / limitations | Known defects / remediation | Evidence reference | Owner / open questions
P01 | Inspection Completion | Proof candidate | [17 empty] | Not deployed or executed; workspace had expired. | Phase 3 closeout context; verify against repo | Re-establish source, owner, use, and execution environment.
P02 | Application Processing Time | Proof candidate | [17 empty] | Deterministic proof outstanding. | Phase 3 closeout context; verify against repo | Identify source, owner, business definition, output, and criteria.
P03 | Portability Activity | Proof candidate | [17 empty] | Deterministic proof outstanding. | Phase 3 closeout context; verify against repo | Identify source, owner, business definition, output, and criteria.